## Sheet1
CW 2.o Updates
Topics | Website | Lead | URL | % Complete | Expected Date | Current Tasks | Next Tasks | Open Issues | Additional Info
Sensor
Design/ Developement Updates
Topics | Website | Lead | URL | % Complete | Expected Date | Current Tasks | Next Tasks | Open Issues | Additional Info
Corporate | Add Veterans section to Careers | Divya | https://curtisswright.com/careers/ | 12% | TBD | Working on the Military Pathways landing page mockup design. Added new Analyst to the Analyst coverage page table.
Defense
EMS |  | Britto | https://electro-mechanicalsystems.curtisswright.com/ | — |  |  | — | — | —
Industrial | [5 empty] | Created two new 2026 Rehacare form page and making few tweaks. Started updating the new brochrues on live site.
Nuclear | Integrate ultra.energy (cwic.curtisswright.com) |  | — | — |  |  | - | —
| Integrate 3keysoft.com / ws-corp.com | Sunil
Integrate cw-connect.com
Evaluate store.ultra.energy (cwicstore.curtsisswright.com)
Sensors & Actuation | Model & Price Configurator new products (GSX, GSM, KX, SLM, SLG, T2X, R2G, R2M, RDG, and RDM). | Rohan | — | 100% | 24th July 2026 | Pushed to live on 24th July 2026
| Model & Price Configurator CRM API | Rohan |  | 100% | 11th August 2026 | Completed Configurator API Updates.
| Integrate tools.exlar.com | Rohan | https://tools.exlar.com | — | TBD | Under Research Analyzing the site. | - | - | -
| Add LMS to Portal | Rohan |  | 90% | TBD | Waiting for boonie's feedback
| Evaluate cw-mro.com |  |  | — | TBD
Surface Tech | CWST Translations | Sindhu | https://cwstcomstage.prod.acquia-sites.com/ | 100% 95% | TBD | Completed the Hungarian translation for the whole CWST website. Started updating the links on all the translated pages. |  | None
| Add RFQ Process | Divya | https://surfacetechnologies.curtisswright.com/contact-us | 100% | TBD | Working on Home page layout Design completed (02/52) layout. completed (0/183) pages. | Integration complete QA & redirects. | —
| Add Searchable approvals database | Divya | — | 20% | TBD | Instlled the required modules and data mapping is completed. working on the view function. | Integration complete QA & redirects.
| IMR Test Labs | Shilpa | https://imrtest.com/ | — | TBD | Working on Home page layout Design completed (02/52) layout. completed (0/183) pages. | Pending layouts: 50/52 Pending Pages : 182/182 | —
| Evaluate everlubeproducts.com | Divya | https://everlubeproducts.com/ | 100% |  | Completed Everlube products site Site Summary Document.
| Evaluate Keronite.com | Britto | https://www.keronite.com/ | 100% | TBD | Completed Keronite site Site Summary Document.
| Evaluate emcoatingsuk.co.uk |  | emcoatingsuk.co.uk | — | TBD
Valves | Add Farris CAD Library | Divya | https://cwvalvescomstage.prod.acquia-sites.com/ | 100% | TBD | The CAD Models & Drawings tab login functionality has been implemented on the live site. | - | - | -
Additional Notes :
SEO: Working on press release title and date appending.(completed years 2002 to 2020). Completed Testing 2015 to 2020 press release title and date appending.
SEO: Working on Web refresh for CW & working on meta title,description for CWST
CW Division sites web refresh: Completed - EMS, Valves, Nuclear and CWST. Working on - Actuation, CW and Sensors site.
CWST : Started testing the CW 2.0 Color Web Refresh for the French and German languages. Updates New line cards links in the location page.
CW Actuation : Started testing the CW 2.0 color web refresh.
CW Nuclear : Started testing the CW 2.0 color web refresh.
Acquia: Working on fixing the bot traffic reduction task list.
Actuation Portal: Working on the standardization of dropdowns in the Price Configurator.
Searchstax : We are updating the latest cw_search module across all live site environments.
CW-Valves : Updated address for the Vector Process Solutions Inc for contact us page and Global Supplier Network map Page.
CW-EST : Updated the DC2561 document on the GripTight Elbow Test Plug product page, Hydrostatic Test Isolation Plugs Documentation Library page, and GripTight Elbow Test Plug SalesHUB page.
CW-EST : Updated the DC8051 link on the OD GripTight Plug SalesHUB page with the correct EST Library PDF link.